# A Yearly Workplan for a Nonprofit Board

Sample

| Major Board Initiatives | Who’s Responsible | Activities | Time Frame | Deliverable(s) | Mid-Year Check |
| --- | --- | --- | --- | --- | --- |
| Create new 3- year Strategic Plan | - Ad Hoc Task Force - Full Board Input - Full Board approval | - Appoint Task Force - Review progress of past plan - Assess relevancy of past goals - Hire consultant - Schedule of input meetings - Identify Opportunities - Set goals and strategies - Identify realistic deliverables | January 2025 to October 2025 | Approved dynamic and relevant 3-year working Strategic Plan that staff and board are enthused about and ready to tackle. | Chair and Board review progress of work plan at 6-month mark and make changes as needed. |
| Reach fundraising goals | - Partnership between Fund Development Committee and Senior Staff - Full Board approval and engagement | - Board attends/supports events - 5 individual board members host 5 small mission events - CEO/chair meet with 25 donors - Secure past donors’ gifts - Expand donor base by 25% | Calendar Year | Funding goals met or exceeded |  |
| CEO Annual Evaluation | - Governance Committee - Board surveyed | - Assess tools - Gain CEO input/Survey Board - Tabulate results/meet with CEO - Set salary for coming year | By May 5, 2025 | CEO provided with quality experience and performance plan for 2017 |  |
| Policy Platform | Advocacy Committee with Staff/Board Approval | - Assess policy issues - Input from board, staff & experts - Design and approve platform | By January 30, 2025 | Policy Platform in Place |  |
| Recruit and engage 3 new board members | - Governance Committee Input - Full Board approval | - Fill out board matrix - Board and CEO input - Board follows recruitment and nomination policy and procedures | By November 2025 | Board recruitment goals met |  |

| Standard Board Business | Who’s Responsible | Activities | Time Frame | Deliverable(s) | Mid-Year Check |
| --- | --- | --- | --- | --- | --- |
| Financials are up to date reviewed and approved by Board | - Finance Committee - With CEO and staff - Board review approval | - Monthly Com. mtgs. - Review/Assess fiscal issues - Report development | Bi-monthly | Clear, updated balanced Financials |  |
| Audit Completed | - Audit Committee - Full board review/ approval | - 3 committee mtgs. - meet with Auditors - Board input/approval | April-June | Audit concluded |  |
| Committee Chairs & Members are assigned and have goals for year meetings scheduled | - Board Chair - Committee Chairs | - Chair assigned; goals set - plan for committee set - committee assumes role - keeps board abreast of progress and issues | January | Committees engaged and meeting goals |  |
| Board Officers are in place | - Full Board | - Potential new leaders are identified, recruited, and mentored - Board engages in nomination process | June December | Board Officers in Place |  |
| Board Members kept abreast of organization news | - CEO - Board Chair | - Board newsletter - CEO reports - Board Updates | Ongoing | Board informed of org. issues and accomplishments. |  |
| Board Meetings scheduled, agenda set, packets delivered | - Board Chair in partnership with CEO | - Annual Board agenda prepared and distributed early - Chair prepares with CEO - Agenda with substance - Board prepared for meeting | November Bi-Monthly | Effective Board Meetings |  |
| Governance Committee maps out yearly Board training & implements | - Governance Committee | - Board meetings include 15 minute of board training - Board retreat occurs | January - ongoing | Engaged, educated Board that understands its role |  |
| Board is prepared and participates in donor cultivation, stewardship & events | - Fund Develop. Com. - CEO /fund dev. staff | - Board fundraising training, - Plans for each strategy presented to board. | Throughout the year | Board effective in Fundraising |  |